## Expenses
BETRESHORI BASIC SCHOOL BUILDING, SINDHUPALCHOWK
Construction Expenses
S. No. | Particulars | Date of evident | Unit | Quantity | Total |  | Rate (NRs.) | Amount | Remarks
[5 empty] | Quantity | Amount
1 | Physical effort
1.1 | Petty Contract up to Plinth Level (Prop. Mr. Bir Bahadur Tamang) | 2075-06-15 | Job | 1 | 1 | 0 | 350000 | 350000 | Contract attached
1.2 | Labour payment | Chaitra, 075 | Month | 1 |  |  | 110550 | 110550 | Mustar Roll attached
1.3 | Labour payment | Baishakh, 076 | Month | 1 |  |  | 208450 | 208450 | Mustar Roll attached
1.4 | Labour payment | Jestha, 076 | Month | 1 |  |  | 268350 | 268350 | Mustar Roll attached
1.5 | Labour payment | Asar, 076 | Month | 1 |  |  | 9600 | 9600 | Mustar Roll attached
2 | Tools and Plant |  |  | 0 | 0 | 0 |  | 0
2.1 | JCB for Earthwork | 2075-06-13 | Lot | 1 | 0 | 0 | 233910 | 233910 | Bill attached
2.2 | Hilltake tank | 2075-07-29 | Lot | 1 | 0 | 0 | 12430 | 12430 | Bill attached
2.3 | Transportation | 2076-01-30 | Lot | 1 |  |  | 102000 | 102000 | Bill attached
2.4 | Transportation | 2076-02-21 | Trip | 21 |  |  | 3000 | 63000 | Bill attached
2.5 | Transportation of cement and bars | 2076-01-13 | Trip | 2 |  |  | 3500 | 7000 | Bill attached
0
3 | Construction Material |  |  | 0 | 0 | 0 |  | 0
3.01 | Sand | 2075-07-28 | Lot | 1 | 0 | 0 | 34171.02 | 34171.02 | Bill attached
3.02 | Reinforcement and cement | 2075-07-28 | Lot | 1 |  |  | 272339.04 | 272339.04 | Bill attached
3.03 | Reinforcement and cement | 2075-08-03 | Lot | 1 |  |  | 222558.02 | 222558.02 | Bill attached
3.04 | Sand | 2075-08-03 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.05 | Aggregate | 2075-08-08 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.06 | Aggregate | 2075-08-09 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.07 | Aggregate | 2075-08-09 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.08 | Sand | 2075-08-11 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.09 | Sand | 2075-08-11 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.1 | Sand | 2075-08-15 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.11 | Cement | 2075-08-16 | Lot | 1 |  |  | 224671.12 | 224671.12 | Bill attached
3.12 | Sand | 2075-08-18 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.13 | Sand | 2075-08-18 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.14 | Aggregate | 2075-08-21 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.15 | Aggregate | 2075-08-26 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.16 | Stone | 2075-09-07 | Trip | 15 |  |  | 7500 | 112500 | Bill attached
3.17 | Stone | 2075-08-08 | Lot | 7 |  |  | 7500 | 52500 | Bill attached
3.18 | CGI Sheet | 2075-08-01 | Lot | 1 |  |  | 14690 | 14690 | Bill attached
3.19 | Forms wood | 2075-07-18 | Lot | 1 |  |  | 59325 | 59325 | Bill attached
3.2 | Aggregate | 2075-09-13 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.21 | Aggregate | 2075-09-10 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.22 | Aggregate | 2075-08-18 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.23 | Aggregate | 2075-09-13 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.24 | Cement | 2075-09-03 | Lot | 1 |  |  | 74231 | 74231 | Bill attached
3.25 | Sand | 2075-09-08 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.26 | Cement | 2075-09-11 | Lot | 1 |  |  | 83620 | 83620 | Bill attached
3.27 | Reinforcement | 2075-09-15 | Lot | 1 |  |  | 170650.34 | 170650.34 | Bill attached
3.28 | Sand | 2075-09-15 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.29 | Binding wire | 2076-01-21 | Lot | 1 |  |  | 3200 | 3200 | Bill attached
3.3 | Brick | 2076-01-06 | Lot | 1 |  |  | 64975 | 64975 | Bill attached
3.31 | Brick | 2076-01-09 | Lot | 1 |  |  | 64975 | 64975 | Bill attached
3.32 | Aggregate | 2076-01-05 | Lot | 1 |  |  | 5000 | 5000 | Bill attached
3.33 | Aggregate | 2076-01-05 | Lot | 1 |  |  | 3389 | 3389 | Bill attached
3.34 | Sand | 2076-01-04 | Lot | 1 |  |  | 4670 | 4670 | Bill attached
3.35 | Sand | 2076-01-04 | Lot | 1 |  |  | 1095 | 1095 | Bill attached
3.36 | Sand | 2076-01-16 | Lot | 2 |  |  | 7500 | 15000 | Bill attached
3.37 | Sand | 2076-01-19 | Lot | 7 |  |  | 13000 | 91000 | Bill attached
3.38 | Pipe, Nails and others | 2076-01-20 | Lot | 1 |  |  | 3370 | 3370 | Bill attached
3.39 | Jalee and Doko | No date | Lot | 1 |  |  | 820 | 820 | Bill attached
3.4 | Sand | 2076-01-13 | Lot | 2 |  |  | 7000 | 14000 | Bill attached
3.41 | Sand | 2076-01-16 | Lot | 2 |  |  | 7500 | 15000 | Bill attached
3.42 | Reinforcement and cement | 2075-02-15 | Lot | 1 |  |  | 159256.55 | 159256.55 | Bill attached
3.43 | Aggregate | 2075-12-19 | Lot | 1 |  |  | 4000.2 | 4000.2 | Bill attached
3.44 | Nails and others | 2076-02-07 | Lot | 1 |  |  | 2070 | 2070 | Bill attached
3.45 | Reinforcement and cement | 2076-02-14 | Lot | 1 |  |  | 154179.78 | 154179.78 | Bill attached
3.46 | Reinforcement | 2076-01-25 | Lot | 1 |  |  | 150064.97 | 150064.97 | Bill attached
3.47 | Reinforcement and cement | 2076-02-02 | Lot | 1 |  |  | 121137.46 | 121137.46 | Bill attached
3.48 | Aggregate | 2076-01-22 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.49 | DDC Tax | 2076-01-22 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.5 | Aggregate | 2076-01-27 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.51 | DDC Tax | 2076-01-27 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.52 | Aggregate | 2076-02-08 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.53 | DDC Tax | 2076-02-08 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.54 | Sand | 2076-02-08 | Lot | 1 |  |  | 12000 | 12000 | Bill attached
3.55 | Pipe, Nails and others | 2076-01-25 | Lot | 1 |  |  | 3674 | 3674 | Bill attached
3.56 | Binding wire | 2076-02-16 | Lot | 1 |  |  | 2115 | 2115 | Bill attached
3.57 | Aggregate | 2075-12-19 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.58 | DDC Tax | 2075-12-19 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.59 | Aggregate | 2076-01-27 | Lot | 1 |  |  | 4000 | 4000 | Bill attached
3.6 | Aggregate | 2076-01-26 | Lot | 1 |  |  | 4500 | 4500 | Bill attached
3.61 | Aggregate | 2076-01-24 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.62 | DDC Tax | 2076-01-24 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.63 | Sand | 2075-11-15 | Lot | 1 |  |  | 4950 | 4950 | Bill attached
3.64 | Sand | 2075-11-15 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.65 | DDC Tax | 2075-11-15 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.66 | Sand | 2075-11-13 | Lot | 1 |  |  | 2880 | 2880 | Bill attached
3.67 | DDC Tax | 2075-11-13 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.68 | Sand | 2075-11-13 | Lot | 1 |  |  | 5000 | 5000 | Bill attached
3.69 | Aggregate | 2076-01-24 | Lot | 1 |  |  | 1095 | 1095 | Bill attached
3.7 | Aggregate | 2075-11-15 | Lot | 1 |  |  | 5000 | 5000 | Bill attached
3.71 | Brick | 2076-02-07 | Lot | 1 |  |  | 24995.6 | 24995.6 | Bill attached
3.72 | DDC Tax | 2076-02-07 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.73 | Sand | 2076-02-07 | Lot | 1 |  |  | 12000 | 12000 | Bill attached
3.74 | Sand | 2076-02-07 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.75 | Sand | 2075-11-14 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.76 | DDC Tax | 2075-11-14 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.77 | Aggregate | 2076-01-24 | Lot | 1 |  |  | 2000 | 2000 | Bill attached
3.78 | DDC Tax | 2076-01-24 | Lot | 1 |  |  | 170 | 170 | Bill attached
3.79 | Stone | 2076-01-18 | Trip | 1 |  |  | 7500 | 7500 | Bill attached
3.8 | Stone | 2076-01-02 | Trip | 4 |  |  | 7500 | 30000 | Bill attached
3.81 | Stone | 2076-01-09 | Trip | 2 |  |  | 7500 | 15000 | Bill attached
3.82 | Stone | 2076-01-14 | Trip | 3 |  |  | 7500 | 22500 | Bill attached
3.83 | Stone | 2076-01-18 | Trip | 3 |  |  | 7500 | 22500 | Bill attached
3.84 | Sand | 2076-01-19 | Trip | 18 |  |  | 3000 | 54000 | Bill attached
0
| Total |  |  |  |  | 0 |  | 4377647.1
[7 empty] | a) 1st lot interim advance from NRNA | 1695000
[7 empty] | b) 2nd lot interim advance from NRNA | 1520000
[7 empty] | c) Contribution from School | 800000
[7 empty] | D) Due payment | 362647.1
[7 empty] | Total Fund = | 4377647.1
Formulas:
Date of evident = [Date of evident, row above]

## Labour
BETRESHORI BASIC SCHOOL BUILDING, SINDHUPALCHOWK
Construction Expenses
S. No. | Particulars | Date of evident | Unit | Quantity | Total |  | Rate (NRs.) | Amount | Remarks
[5 empty] | Quantity | Amount
1 | Physical effort
1.1 | Petty Contract up to Plinth Level (Prop. Mr. Bir Bahadur Tamang) | 2075-06-15 | Job | 1 | 1 | 0 | 350000 | 350000 | Contract attached
1.2 | Labour payment | Chaitra, 075 | Month | 1 |  |  | 110550 | 110550 | Mustar Roll attached
1.3 | Labour payment | Baishakh, 076 | Month | 1 |  |  | 208450 | 208450 | Mustar Roll attached
1.4 | Labour payment | Jestha, 076 | Month | 1 |  |  | 268350 | 268350 | Mustar Roll attached
1.5 | Labour payment | Asar, 076 | Month | 1 |  |  | 9600 | 9600 | Mustar Roll attached
0
| Total |  |  |  |  | 0 |  | 946950

## Trans
BETRESHORI BASIC SCHOOL BUILDING, SINDHUPALCHOWK
Construction Expenses
S. No. | Particulars | Date of evident | Unit | Quantity | Total |  | Rate (NRs.) | Amount | Remarks
[5 empty] | Quantity | Amount
2 | Tools and Plant |  |  | 0 | 0 | 0 |  | 0
2.1 | JCB for Earthwork | 2075-06-13 | Lot | 1 | 0 | 0 | 233910 | 233910 | Bill attached
2.2 | Hilltake tank | 2075-07-29 | Lot | 1 | 0 | 0 | 12430 | 12430 | Bill attached
2.3 | Transportation | 2076-01-30 | Lot | 1 |  |  | 102000 | 102000 | Bill attached
2.4 | Transportation | 2076-02-21 | Trip | 21 |  |  | 3000 | 63000 | Bill attached
2.5 | Transportation of cement and bars | 2076-01-13 | Trip | 2 |  |  | 3500 | 7000 | Bill attached
0
| Total |  |  |  |  | 0 |  | 418340

## Sand
BETRESHORI BASIC SCHOOL BUILDING, SINDHUPALCHOWK
Construction Expenses
S. No. | Particulars | Date of evident | Unit | Quantity | Total |  | Rate (NRs.) | Amount | Remarks
[5 empty] | Quantity | Amount
3 | Construction Material |  |  | 0 | 0 | 0 |  | 0
3.01 | Sand | 2075-07-28 | Lot | 1 | 0 | 0 | 34171.02 | 34171.02 | Bill attached
3.04 | Sand | 2075-08-03 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.08 | Sand | 2075-08-11 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.09 | Sand | 2075-08-11 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.1 | Sand | 2075-08-15 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.12 | Sand | 2075-08-18 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.13 | Sand | 2075-08-18 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.25 | Sand | 2075-09-08 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.28 | Sand | 2075-09-15 | Lot | 1 |  |  | 34171 | 34171 | Bill attached
3.34 | Sand | 2076-01-04 | Lot | 1 |  |  | 4670 | 4670 | Bill attached
3.35 | Sand | 2076-01-04 | Lot | 1 |  |  | 1095 | 1095 | Bill attached
3.36 | Sand | 2076-01-16 | Lot | 2 |  |  | 7500 | 15000 | Bill attached
3.37 | Sand | 2076-01-19 | Lot | 7 |  |  | 13000 | 91000 | Bill attached
3.4 | Sand | 2076-01-13 | Lot | 2 |  |  | 7000 | 14000 | Bill attached
3.41 | Sand | 2076-01-16 | Lot | 2 |  |  | 7500 | 15000 | Bill attached
3.54 | Sand | 2076-02-08 | Lot | 1 |  |  | 12000 | 12000 | Bill attached
3.63 | Sand | 2075-11-15 | Lot | 1 |  |  | 4950 | 4950 | Bill attached
3.64 | Sand | 2075-11-15 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.65 | DDC Tax | 2075-11-15 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.66 | Sand | 2075-11-13 | Lot | 1 |  |  | 2880 | 2880 | Bill attached
3.67 | DDC Tax | 2075-11-13 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.68 | Sand | 2075-11-13 | Lot | 1 |  |  | 5000 | 5000 | Bill attached
3.73 | Sand | 2076-02-07 | Lot | 1 |  |  | 12000 | 12000 | Bill attached
3.74 | Sand | 2076-02-07 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.75 | Sand | 2075-11-14 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.76 | DDC Tax | 2075-11-14 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.84 | Sand | 2076-01-19 | Trip | 18 |  |  | 3000 | 54000 | Bill attached
0
| Total |  |  |  |  | 0 |  | 549301.02
Formulas:
Date of evident = [Date of evident, row above]

## Cement
BETRESHORI BASIC SCHOOL BUILDING, SINDHUPALCHOWK
Construction Expenses
S. No. | Particulars | Date of evident | Unit | Quantity | Total |  | Rate (NRs.) | Amount | Remarks
[5 empty] | Quantity | Amount
3 | Construction Material |  |  | 0 | 0 | 0 |  | 0
3.02 | Reinforcement and cement | 2075-07-28 | Lot | 1 |  |  | 272339.04 | 272339.04 | Bill attached
3.03 | Reinforcement and cement | 2075-08-03 | Lot | 1 |  |  | 222558.02 | 222558.02 | Bill attached
3.24 | Cement | 2075-09-03 | Lot | 1 |  |  | 74231 | 74231 | Bill attached
3.26 | Cement | 2075-09-11 | Lot | 1 |  |  | 83620 | 83620 | Bill attached
3.27 | Reinforcement | 2075-09-15 | Lot | 1 |  |  | 170650.34 | 170650.34 | Bill attached
3.42 | Reinforcement and cement | 2075-02-15 | Lot | 1 |  |  | 159256.55 | 159256.55 | Bill attached
3.45 | Reinforcement and cement | 2076-02-14 | Lot | 1 |  |  | 154179.78 | 154179.78 | Bill attached
3.46 | Reinforcement | 2076-01-25 | Lot | 1 |  |  | 150064.97 | 150064.97 | Bill attached
3.47 | Reinforcement and cement | 2076-02-02 | Lot | 1 |  |  | 121137.46 | 121137.46 | Bill attached
3.56 | Binding wire | 2076-02-16 | Lot | 1 |  |  | 2115 | 2115 | Bill attached
0
| Total |  |  |  |  | 0 |  | 1410152.16

## Aggregate
BETRESHORI BASIC SCHOOL BUILDING, SINDHUPALCHOWK
Construction Expenses
S. No. | Particulars | Date of evident | Unit | Quantity | Total |  | Rate (NRs.) | Amount | Remarks
[5 empty] | Quantity | Amount
3 | Construction Material |  |  | 0 | 0 | 0 |  | 0
3.05 | Aggregate | 2075-08-08 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.06 | Aggregate | 2075-08-09 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.07 | Aggregate | 2075-08-09 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.14 | Aggregate | 2075-08-21 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.15 | Aggregate | 2075-08-26 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.2 | Aggregate | 2075-09-13 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.21 | Aggregate | 2075-09-10 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.22 | Aggregate | 2075-08-18 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.23 | Aggregate | 2075-09-13 | Lot | 1 |  |  | 30800 | 30800 | Bill attached
3.32 | Aggregate | 2076-01-05 | Lot | 1 |  |  | 5000 | 5000 | Bill attached
3.33 | Aggregate | 2076-01-05 | Lot | 1 |  |  | 3389 | 3389 | Bill attached
3.43 | Aggregate | 2075-12-19 | Lot | 1 |  |  | 4000.2 | 4000.2 | Bill attached
3.48 | Aggregate | 2076-01-22 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.49 | DDC Tax | 2076-01-22 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.5 | Aggregate | 2076-01-27 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.51 | DDC Tax | 2076-01-27 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.52 | Aggregate | 2076-02-08 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.53 | DDC Tax | 2076-02-08 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.57 | Aggregate | 2075-12-19 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.58 | DDC Tax | 2075-12-19 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.59 | Aggregate | 2076-01-27 | Lot | 1 |  |  | 4000 | 4000 | Bill attached
3.6 | Aggregate | 2076-01-26 | Lot | 1 |  |  | 4500 | 4500 | Bill attached
3.61 | Aggregate | 2076-01-24 | Lot | 1 |  |  | 3050 | 3050 | Bill attached
3.62 | DDC Tax | 2076-01-24 | Lot | 1 |  |  | 339 | 339 | Bill attached
3.69 | Aggregate | 2076-01-24 | Lot | 1 |  |  | 1095 | 1095 | Bill attached
3.7 | Aggregate | 2075-11-15 | Lot | 1 |  |  | 5000 | 5000 | Bill attached
3.77 | Aggregate | 2076-01-24 | Lot | 1 |  |  | 2000 | 2000 | Bill attached
3.78 | DDC Tax | 2076-01-24 | Lot | 1 |  |  | 170 | 170 | Bill attached
0
| Total |  |  |  |  | 0 |  | 323299.2
Formulas:
Date of evident = [Date of evident, row above]

## Brick
BETRESHORI BASIC SCHOOL BUILDING, SINDHUPALCHOWK
Construction Expenses
S. No. | Particulars | Date of evident | Unit | Quantity | Total |  | Rate (NRs.) | Amount | Remarks
[5 empty] | Quantity | Amount
3 | Construction Material |  |  | 0 | 0 | 0 |  | 0
3.3 | Brick | 2076-01-06 | Lot | 1 |  |  | 64975 | 64975 | Bill attached
3.31 | Brick | 2076-01-09 | Lot | 1 |  |  | 64975 | 64975 | Bill attached
3.71 | Brick | 2076-02-07 | Lot | 1 |  |  | 24995.6 | 24995.6 | Bill attached
3.72 | DDC Tax | 2076-02-07 | Lot | 1 |  |  | 339 | 339 | Bill attached
0
| Total |  |  |  |  | 0 |  | 155284.6 |  | 12.94
Formulas:
Date of evident = [Date of evident, row above]

## ST-1 (hidden)
#REF! | [13 empty] | 0
Quantity Estimate (Septic Tank - Type : 1)
S.No. | Item | Item code | Nos. | Length | Breadth | Height | Quantity | Unit | Sub | Item | Rate | Amount | Remarks
[9 empty] | Total | Total
1.1 | EARTHWORK AND SAND FILLING
1.1.2 |  | 1.1.1 | [6 empty] | 5.817 | 5.817
| Foundation |  | 1 | 2.95 | 1.7 | 1.16 | 5.817
1.1.3 |  | 1.1.2 | [7 empty] | 0.962
| Total Excavation | [5 empty] | 5.817 |  | 0.962
Deduction
| Septic tank |  | 1 | 2.75 | 1.5 | 1 | -4.125
| Base slab & Brick soling |  | 1 | 2.85 | 1.6 | 0.16 | -0.73
1.2 | BRICK WORK
1.2.1 |  | 1.2.2 | [7 empty] | 4.56
4.56
|  |  | 1 | 2.85 | 1.6 |  | 4.56
1.2.2 |  | 1.2.3 | [7 empty] | 2.125
| Wall | [7 empty] | 2.125
| Long wall |  | 2 | 2.75 | 0.25 | 1 | 1.375
| Short wall |  | 2 | 1 | 0.25 | 1 | 0.5
|  |  | 1 | 1 | 0.25 | 0.7 | 0.175
|  |  | 1 | 0.4 | 0.25 | 0.3 | 0.03
| Honeycomb Wall |  | 1 | 0.6 | 0.25 | 0.3 | 0.045
1.3 | PCC, RCC and Pre-cast Cement Work
1.3.1 |  | 1.3.6 | [7 empty] | 0.951
0.951
| Base Slab |  | 1 | 2.85 | 1.6 | 0.1 | 0.456
| Precast Slab |  | 3 | 1.5 | 0.6 | 0.12 | 0.324
|  |  | 2 | 1.5 | 0.475 | 0.12 | 0.171
| Precast cover |  | 1 | 0.2 | 0.2 | 0.075 | 0.003
| Deduction of Precast hole |  | 1 | 0.15 | 0.15 | 0.12 | -0.003
1.3.2 |  | 1.3.3 | Details are shown on Bar bending sheet |  |  |  | 0.062 |  | 0.062 | 0.062
1.3.3 |  | 1.3.4 | [7 empty] | 3.442
| Base Slab |  | 2 | 2.75 |  | 0.1 | 0.55 |  | 3.442
|  |  | 2 | 1.5 |  | 0.1 | 0.3
| Precast Slab |  | 3 | 4.2 |  | 0.12 | 1.512
|  |  | 2 | 3.95 |  | 0.12 | 0.948
| Precast cover |  | 1 | 0.8 |  | 0.075 | 0.06
| hole |  | 1 | 0.6 |  | 0.12 | 0.072
1.4 | Plastering and Finishing Works
1.4.1 |  | 1.4.2 | [7 empty] | 10
| Inner Wall |  | 2 | 4 |  | 1 | 8 |  | 10
| Base |  | 2 | 1 | 1 |  | 2
1.4.4 |  | 1.4.9 | [7 empty] | 10
|  |  | Same as Plastering |  |  |  | 10 |  | 10

## ST-1_Rein (hidden)
#REF!
Bar Bending Schedule for Septic Tank (Type-1)
SN | Descriptions | No. | Bars | Dia | Length | Total Bars | T.Length | Weight | Total Wt. | Bars Sketch
|  |  | No. | mm | m | No. | m | Kg/m | Kg
1 | Base Slab
| Top bar | 1 | 16 | 8 | 1.71 | 16 | 27.36 | 0.4 | 10.944
|  | 1 | 9 | 8 | 2.96 | 9 | 26.64 | 0.4 | 10.656
2 | Precast Cover Slab
| Bottom bar | 3 | 11 | 8 | 0.71 | 33 | 23.43 | 0.4 | 9.372
|  | 3 | 5 | 10 | 1.65 | 15 | 24.75 | 0.62 | 15.345
|  | 2 | 11 | 8 | 0.59 | 22 | 12.98 | 0.4 | 5.192
|  | 2 | 5 | 10 | 1.65 | 10 | 16.5 | 0.62 | 10.23
[8 empty] | Total | 61.739

## Inspection (hidden)
GAJURI HOSPITAL BUILDING | [13 empty] | 1818.17
Inspection Chamber
S.No. | Item | Item code | Nos. | Length | Breadth | Height | Quantity | Unit | Sub | Item | Rate | Amount | Remarks
[9 empty] | Total | Total
1.1 | EARTHWORK AND SAND FILLING
1.1.1 | Earthwork in excavation | 1.1.1 | [5 empty] | cum | 0.32 | 0.32 | 74.62 | 23.88
| Foundation |  | 1 | 0.8 | 0.8 | 0.5 | 0.32
1.1.2 | Earthwork in filling | 1.1.2 | [5 empty] | cum |  | 0.039 | 70.55 | 2.75
| Total Excavation | [5 empty] | 0.32 |  | 0.039
Deduction
| Chamber |  | 1 | 0.7 | 0.7 | 0.365 | -0.179
| Base slab & Brick soling |  | 1 | 0.8 | 0.8 | 0.16 | -0.102
1.2 | BRICK WORK
1.2.1 | Flat brick soling | 1.2.2 | [5 empty] | sqm |  | 0.64 | 192.97 | 123.5
0.64
|  |  | 1 | 0.8 | 0.8 |  | 0.64
1.2.2 | Brick work in CM(1:4) | 1.2.3 | [5 empty] | cum |  | 0.13 | 3331.55 | 433.1
| Wall | [7 empty] | 0.13
| Long wall |  | 2 | 0.7 | 0.125 | 0.45 | 0.079
| Short wall |  | 2 | 0.45 | 0.125 | 0.45 | 0.051
1.3 | PCC, RCC and Pre-cast Cement Work
1.3.1 | PCC M15 work | 1.3.6 | [5 empty] | cum |  | 0.097 | 4089.06 | 396.64
0.097
| Base Slab |  | 1 | 0.8 | 0.8 | 0.075 | 0.048
| Precast Slab |  | 1 | 0.7 | 0.7 | 0.1 | 0.049
1.3.2 | Reinforcement work | 1.3.3 | steel bars @100kg per cum |  |  |  | 0.01 | ton | 0.01 | 0.01 | 45988.5 | 459.89
1.3.3 | Shuttering work with plywood and steel props | 1.3.4 | [5 empty] | sqm |  | 0.56 | 354.91 | 198.75
| Base Slab |  | 2 | 0.8 |  | 0.075 | 0.12 |  | 0.56
|  |  | 2 | 0.8 |  | 0.075 | 0.12
| Precast Slab |  | 1 | 3.2 |  | 0.1 | 0.32
1.4 | Plastering and Finishing Works
1.4.1 | 20mm thick plaster on floor and wall | 1.4.2 | [5 empty] | sqm |  | 1.013 | 117.57 | 119.1
| Inner Wall |  | 1 | 1.8 |  | 0.45 | 0.81 |  | 1.013
| Base |  | 1 | 0.45 | 0.45 |  | 0.203
1.4.4 | 3mm Punning work | 1.4.9 | [5 empty] | sqm |  | 1.01 | 59.96 | 60.56
|  |  | Same as Plastering |  |  |  | 1.013 |  | 1.01

## Wast_Pit (hidden)
GAJURI HOSPITAL BUILDING | [13 empty] | 10.67
Sharp waste pit
S.No. | Item | Item code | Nos. | Length | Breadth | Height | Quantity | Unit | Sub | Item | Rate | Amount | Remarks
[9 empty] | Total | Total
1.1 | EARTHWORK AND SAND FILLING
1.1.1 | Earthwork in excavation | 1.1.1 | [5 empty] | cum | 0.143 | 0.143 | 74.62 | 10.67
| Foundation |  | 1 | Area = | 0.075 | 1.9 | 0.143
1.3 | PCC, RCC and Pre-cast Cement Work
1.3.1 | 300 Dia NP2 Concrete pipe | [6 empty] | No. |  | 1
|  |  | 1 |  |  |  | 1 |  | 1
1.4 | 300 Dia MS Cover |  | 1 |  |  |  | 1 | No. |  | 1

## Input (hidden)
All dimensions are in metric unit
Foundation Datas | [7 empty] | Grid Lengths |  |  |  | Wall |  |  | Thickness | [5 empty] | Wall Heights |  |  | Doors and Windows |  |  |  | No's |  | Grill Wt.
Isolated footings | [7 empty] | g1-1 | 15.43 | ga'-a' | 12.7 | wth1 | 0.125 |  | thk1 | 0.075 |  | earthfill | 0.41 |  | hit1 | 2.95 |  | d1b | 1.5 | d1h | 2.1 | d1n | 1
F1 | 1.5 | fta1b | 2.1 | fta1d | 0.2 | fta1dd | 0.25 | g2-2 | 17.93 | ga-a | 33.65 | wth2 | 0.25 |  | thk2 | 0.1 |  | sandfill | 0.2 |  | hit2 | 2.95 |  | d2b | 1.2 | d2h | 2.1 | d2n | 9 | 90.822 | cm3
F2 | 1.7 | ftd1b | 2.1 | ftd1d | 0.2 | ftd1dd | 0.25 | g3-3 | 17.93 | gb-b | 33.65 | wth3 | 0.38 |  | thk3 | 0.125 |  | pcc1 | 0.15 |  | hit3 |  |  | d2'b | 1.2 | d2'h | 2.1 | d2'n | 1 | 0
F3 | 1.8 | fte1b | 2.1 | fte1d | 0.2 | fte1dd | 0.25 | g4-4 | 13.15 | gc-c | 33.65 | Beams & Slabs | [5 empty] | pcc2 | 0.05 |  | hit4 |  |  | d3b | 1 | d3h | 2.1 | d3n | 2 | 0
F4 | 2 | fta2b | 2.2 | fta2d | 0.2 | fta2dd | 0.25 | g5-5 | 13.15 | gd-d | 22.25 | tbel1 |  | beamd1 | 0.275 | [5 empty] | hit5 |  |  | d4b | 0.75 | d4h | 2.1 | d4n | 3
ftd2l | 2.2 | ftd2b | 2.2 | ftd2d | 0.2 | ftd2dd | 0.25 |  |  | ge-e | 10.35 |  |  | beamd2 | 0.275 | [8 empty] | d5b | 1.75 | d5h | 2.1 | d5n | 1
fte2l | 2.1 | fte2b | 2.1 | fte2d | 0.2 | fte2dd | 0.25 | g6-6 | 10.65 |  |  | sbel1 |  | beamw | 0.25 | [5 empty] | plhit | 0.75 |  | dwb | 2.7 | dwh | 2.1 | dwn | 1
fta3l | 2.1 | fta3b | 2.1 | fta3d | 0.2 | fta3dd | 0.25 |  |  |  |  | lbel1 |  | lbed1 | [6 empty] | tied | 0.35
ftd3l | 2.1 | ftd3b | 2.1 | ftd3d | 0.2 | ftd3dd | 0.25 | g7-7 | 6.85 | [11 empty] | lintd | 0.2 |  | w1b | 2 | w1h | 1.2 | w1n | 11
fte3l | 2 | fte3b | 2 | fte3d | 0.2 | fte3dd | 0.25 | g8-8 | 6.85 |  |  | bel1 |  | bed1 |  |  | 0.14641 | [6 empty] | w2b | 1.2 | w2h | 1.2 | w2n | 3
fta4l | 2.1 | fta4b | 2.1 | fta4d | 0.2 | fta4dd | 0.25 | g9-9 | 6.85 |  |  | bel2 |  | bed2 | [5 empty] | Room Dimension |  |  |  | w3b | 1 | w3h | 1.2 | w3n | 9
ftd4l | 2 | ftd4b | 2 | ftd4d | 0.2 | ftd4dd | 0.25 |  |  |  |  | slab1 | 0.125 | [6 empty] | ward1 | 5.45 | ward2 | 3.95 | v1b | 0.75 | v1h | 0.6 | v1n | 3
fta5l | 2.1 | fta5b | 2.1 | fta5d | 0.2 | fta5dd | 0.25 |  |  |  |  | slab2 | 0.1 | [6 empty] | toil1 | 1.7 | toil2 | 1.65 | v2b/w1 | 2 | v2h/w1 | 0.45 | v2n/w1 | 10
ftd5l | 2 | ftd5b | 2 | ftd5d | 0.2 | ftd5dd | 0.25 |  |  |  |  | Roof Area | [7 empty] | bath1 | 1.53 | bath2 | 1.65 | v2b/w2 | 1.2 | v2h/w2 | 0.45 | v2n/w2 | 2
fta6l | 2 | fta6b | 2 | fta6d | 0.2 | fta6dd | 0.25 |  |  |  |  | Roof1 | 5.0445 | Roof10 | 20.5509 |  |  |  |  | store1 | 3.355 | store2 | 1.63 | v2b/w3 | 1 | v2h/w3 | 0.45 | v2n/w3 | 10
ftd6l | 2 | ftd6b | 2 | ftd6d | 0.2 | ftd6dd | 0.25 |  |  | len-1 | 3.18 | Roof2 | 12.768 | Roof11 | 6.465 |  |  |  |  | predel1 | 3.355 | predel2 | 4.505 | v2b/v1 | 0.75 | v2h/v1 | 0.45 | v2n/v1 | 3
fta7l | 2 | fta7b | 2 | fta7d | 0.2 | fta7dd | 0.25 |  |  | len-2 | 1 | Roof3 | 34.4905 | Roof12 | 10.4764 |  |  |  |  | stoil1 | 1.25 | stoil2 | 3.055 | v2b/dw | 2.7 | v2h/dw | 0.45 | v2n/dw | 1
fta8l | 2 | fta8b | 2 | fta8d | 0.2 | fta8dd | 0.25 |  |  | len-3 | 4.89 | Roof4 | 11.2638 | Roof13 | 23.9811 |  |  |  |  | del1 | 4.03 | del2 | 4.505
fta9l | 2 | fta9b | 2 | fta9d | 0.2 | fta9dd | 0.25 |  |  | len-4 | 2.6 | Roof5 | 16.138 | Roof14 | 21.9748 |  |  |  |  | nurs1 | 4.03 | nurs2 | 3.53 | cgb | 2 | cgh | 2.1
fta'2l | 1.5 | fta'2b | 1.5 | fta'2d | 0.2 | fta'2dd | 0.2 |  |  | len-5 | 3.6 | Roof6 | 27.8418 | Roof15 | 6.4564 |  |  |  |  | adm1 | 4.11 | adm2 | 3.95 | cg1b | 1.2 | cg1h | 2.1
fta'3l | 1.5 | fta'3b | 1.5 | fta'3d | 0.2 | fta'3dd | 0.2 |  |  | len-6 | 7.38 | Roof7 | 15.609 | Roof16 | 21.6574 |  |  |  |  | wait1 | 4 | wait2 | 3.95
fta'4l | 1.5 | fta'4b | 1.5 | fta'4d | 0.2 | fta'4dd | 0.2 |  |  | len-7 | 6.4 | Roof8 | 63.9068 | Roof17 | 30.1424 |  |  |  |  | void1 | 4.03 | void2 | 3.55
fta'5l | 1.5 | fta'5b | 1.5 | fta'5d | 0.2 | fta'5dd | 0.2 |  |  | len-8 | 4.401 | Roof9 | 8.4034 | Roof18 | 4.6171 |  |  |  |  | hedu1 | 5.175 | hedu2 | 3.55
[10 empty] | len-9 | 4.615 |  |  | Roof19 | 18.1908 |  |  |  |  | pha1 | 3.53 | pha2 | 4
Foun_Proj | 0.075 | [12 empty] | Roof20 | 27.4073 |  |  |  |  | cons1 | 3.55 | cons2 | 4
ftbc1l | 2.1 | ftbc1b | 2.1 | ftbc1d | 0.2 | ftbc1dd | 0.25 |  |  |  |  | Roof Inclination |  | Roof21 | 13.7891 |  |  |  |  | cons11 | 3.55 | cons22 | 4
ftbc2l | 2.2 | ftbc2b | 2.2 | ftbc2d | 0.2 | ftbc2dd | 0.25 |  |  |  |  | theta | 17.354 | Roof22 | 7.6137 |  |  |  |  | lab1 | 3.55 | lab2 | 4
ftbc3l | 2.1 | ftbc3b | 2.1 | ftbc3d | 0.2 | ftbc3dd | 0.25 | [6 empty] | Roof23 | 8.7144 |  |  |  |  | cor1 | 33.05 | cor2 | 2
ftbc4l | 2.1 | ftbc4b | 2.1 | ftbc4d | 0.2 | ftbc4dd | 0.25 | [6 empty] | Roof24 | 4.8075 |  |  |  |  | corr1 | 1.875 | corr2 | 5.55
ftbc5l | 2.1 | ftbc5b | 2.1 | ftbc5d | 0.2 | ftbc5dd | 0.25 | [6 empty] | Roof25 | [5 empty] | corrr1 | 1.875 | corrr2 | 3.5
ftbc6l | 2.1 | ftbc6b | 2.1 | ftbc6d | 0.2 | ftbc6dd | 0.25 | [6 empty] | Roof26 | [5 empty] | Dress1 | 3.53 | dress2 | 6.25
ftb789l | 2.1 | ftb789b | 2.1 | ftb789d | 0.2 | ftb789dd | 0.25 | [6 empty] | Roof27
ftc789l | 1.5 | ftc789b | 1.5 | ftc789d | 0.2 | ftc789dd | 0.2
[9 empty] | Floor area | 33.65 | 6.85 | 230.5025 |  | Chhajjas
[10 empty] | 6.4 | 2.5 | 16 |  | plan1 | 10.1553
Excf | 1.5 | [8 empty] | 22.25 | 3.8 | 84.55 |  | plan2 | 9.1299
excw | 0.45 | [8 empty] | 10.35 | 4.75 | 49.1625 |  | plan3 | 2.0868
[12 empty] | 380.215 |  | plan4 | 2.4951 |  |  |  |  | Corridors
[14 empty] | plan5 | 6.4047 |  |  |  |  | col1 | 7.31 | cob1 | 1.2
[14 empty] | plan6 | 3.0786 |  |  |  |  | col2 | 21.075 | cob2 | 2
[20 empty] | col3 | 3.68 | cob3 | 1.2
[20 empty] | col4 | 3.5 | cob4 | 2.8
[20 empty] | col5 | 3.3 | cob5 | 1.5
[20 empty] | col6 | 7.8 | cob6 | 1.6
[20 empty] | col7 | 4.1 | cob7 | 1.05
[20 empty] | col8 | 5.7 | cob8 | 1.5
[20 empty] | col9 | 6.5 | cob9 | 2.2
[20 empty] | col10 | 4.9 | cob10] | 1.2

## Input SQ (hidden)
Doors and Windows
Foundation Data | [5 empty] | Grid Lengths |  |  |  | Wall |  | Beams and Slabs |  |  |  | Floors and Finishing |  | dbl1 | 1.05 | dbh1 | 2.1 | don1 | 2
Step Footings | [5 empty] | g1-1 | 6.05 | ga-a | 10.45 | wth1 | 0.125 |  |  |  |  | earthfill | 0.49 | dbl2 | 0.75 | dbh2 | 2.1 | don2 | 2
|  | Depth |  |  |  | g2-2 | 6.675 | gb-b | 10.45 | wth2 | 0.25 | tbel1 | 0.25 | tbed1 | 0.25 | sandfill | 0.15 | dbl3 |  | dbh3 |  | don3
ftn1 | 0.38 | ftd1 | 0.15 |  |  | g3-3 | 6.675 | gc-c |  | wth3 |  | sbel1 | 0.25 | sbed1 | 0.075 | pcc1 | 0.05 | dbl |  | dbh |  | dwn
ftn2 | 0.25 | ftd2 | 0.65 |  |  | g4-4 | 6.05 | gd-d |  |  |  | lbel1 | 0.25 | lbed1 | 0.2 | pcc2 |  | dwdl |  | dwdh
ftn3 |  | ftd3 |  |  |  | g5-5 |  | ge-e |  | Wall Height |  | bel1 | 0.25 | bed1 | 0.23 |  |  | dwwl |  | dwwh
ftn4 |  | ftd4 | [7 empty] | height1 | 2.95 | bel2 | 0.25 | bed2
ftn5 |  | ftd5 | [7 empty] | height2 | 3.18 | slab1 | 0.12 |  |  |  |  | winb |  | winh |  | win
ftn6 |  | ftd6 |  |  |  | Non- Grid Length |  |  |  | height3 | 1.45 | slab2 | 0.1 |  |  |  |  | winb1 | 1.2 | winh1 | 1.5 | win1 | 6
Column Footing | [5 empty] | len1 | 3.45 | lenb1 | 4.3 | [8 empty] | winb2 |  | winh2 |  | win2
cfnl1 | 1.5 | cfnb1 | 1.5 | cfnd1 | 0.5 | len2 | 3.45 | lenb2 | [9 empty] | venb |  | venh |  | ven
cfnl2 |  | cfnb2 |  |  |  | len3 | 3.45 | lenb3 |  |  |  | Columns | [5 empty] | venb1 | 0.9 | venh1 | 0.45 | ven1 | 2
cfnl3 |  | cfnb3 |  |  |  | len4 |  | lenb4 |  |  |  | col1 | 0.25 | cob1 | 0.3 |  |  | venb2 | 0.6 | venh2 | 0.45 | ven2 | 2
cfnl4 |  | cfnb4 |  |  |  | len5 |  | lenb5 |  |  |  | col2 |  | cob2 |  |  |  | venb3 |  | venh3 |  | ven3
cfnl5 |  | cfnb5 |  |  |  | len6 |  | lenb6 |  |  |  | col3 |  | cob3
[12 empty] | col4 |  | cob4
depth1 | 1.5 |  | 49 | [8 empty] | col5 |  | cob5 |  |  |  | Room Dimension
depth2 | [11 empty] | col6 |  | cob6 |  |  |  | rml1 | 3.2 | rmb1 | 5.75
[12 empty] | col7 |  | cob7 |  |  |  | rml2 | 3.2 | rmb2 | 5.75
[12 empty] | col8 |  | cob8 |  |  |  | rml3 | 2.5 | rmb3 | 1.5
[12 empty] | col9 |  | cob9
[18 empty] | bathl1 | 1.5 | bathb1 | 2
[18 empty] | varl1 | 3.15 | varb1 | 1.75

## Electrical (hidden)
Dhading
Estimate Of Electrical works
Sr. | Description | Unit | Quantities qt | [7 empty] | Qty | Rate | Amount
No |  |  | Medical | Ward | Qtr | Toilet | Ramp | Guard | Existing | Site
1 | Main Control Panel
| Supply, installation and testing of Main Distribution Board l (MDB) Flush Type/Pad mounting type, dust and vermin proof made of 16 SWG mild steelsheet cubical with double cover and locking arrangement as per drawing and specification with followings: | set | [7 empty] | 1 | 1 | 98958 | 98958
Section a ( City Supply)
Incomming
1 x 150A TP MCCB
1 x 60 A TP+N Changeover Switch
Outgoing
3 x 50 A TP MCCB
3 x 30 A TP MCCB
3 x 20 A TP MCCB
1 set of 300 amp TPN copper bus bars
1 set of earth bus bar
1 set of HRC Fuse
1 set of Voltmeter with selector switch
1 set of 200 Amp ammeter with selector switch
- Cable glands for incoming and outgoing cables
Section B ( Geberator Back up)
Incomming
1 x 40A TP MCCB
Outgoing
2 x 25 A TP MCB
2 x 20 A TP MCB
2 x 16 A TP MCB
1 set of 120 amp DP copper bus bars
1 set of earth bus bar
1 set of Voltmeter with selector switch
1 set of 50 Amp ammeter with selector switch
- Cable glands for incoming and outgoing cables
2.1 | Distribution Boards in Medical Service (DB2)/Mixed Ward Block(DB3)
| Supply, installation and testing of Exterior Distribution Board in (EDB) wall (flush) mounting concealed type, dust and vermin proof made of 16 SWG mild steel sheet cubical with double cover covering the MCB's with the locking arrangement as per drawing |  | 1 | 1 | [6 empty] | 2 | 25070 | 50140
Incommer (city supply)
1 no. of 40 A TP MCB (Havells)
Outgoing
4 nos. of 32 A TP MCB Halvells
- 1 set of 100 amp TPN copper bus bars
- 1 no of earth bus bar
Incommer (Generator Supply)
1 no of 25 A TP MCB ( Havells)
Outgoing
4 nos. of 20 A TP MCB Halvells
- 1 set of 75 amp TPN copper bus bars
- 1 no of earth bus bar
2.1.1 | Sub Distribution Boards 21,22,23,24,31,32,33,34 |  | 4 | 4 | [6 empty] | 8 | 19033 | 152264
Supply, installation and testing of Distribution Board in (SDB) wall (flush) mounting concealed type, dust and vermin proof made of 16 SWG mild steel sheet cubical with double cover covering the MCB's with the locking arrangement as per drawing
Incommer (city supply)
20 A TP MCB (Havells)
Outgoing
12 nos. of 16 A SP MCB Halvells
9 nos. of 6 A SP MCB Halvells
- 1 set of 60 amp TPN copper bus bars
- 1 no of earth bus bar
Incommer (Generator Supply)
16 A DP MCB ( Havells)
Outgoing
6 nos. of 10 A SP MCB Halvells
3 nos. of 6 A SP MCB Halvells
- 1 set of 45 amp P+N copper bus bars
- 1 no of earth bus bar
2.3 | Distribution Boards in Toilet Block (DB-4) |  |  |  |  | 1 |  |  |  |  | 1 | 9465 | 9465
Supply, installation and testing of Distribution Board in (DB) wall (flush) mounting concealed type, dust and vermin proof made of 16 SWG mild steel sheet cubical with double cover covering the MCB's with the locking arrangement as per drawing
Incommer (city supply only)
16 A TP MCB (Havells)
Outgoing
6 nos. of 16 A SP MCB Halvells
3 nos. of 6 A SP MCB Halvells
- 1 set of 60 amp TPN copper bus bars
- 1 no of earth bus bar
2.4 | Distribution Boards X - Ray Room (DB-5) |  |  | 1 | [6 empty] | 1 | 23460 | 23460
Supply, installation and testing of Distribution Board in (DB) wall (flush) mounting concealed type, dust and vermin proof made of 16 SWG mild steel sheet cubical with double cover covering the MCB's with the locking arrangement as per drawing
Incommer (city supply only)
30 A TP MCCB
Outgoing
1 nos. of 25 A TP MCB Halvells
3 nos. of 16 A TP MCB Halvells
- 1 set of 80 amp TPN copper bus bars
- 1 no of earth bus bar
- 1 set of 75 amp TPN copper bus bars
- 1 no of earth bus bar
- 1 set of Indicator Lamp
2.5 | Distribution Boards Out Door Development
| Supply, installation and testing of Distribution Board in (DB) wall (flush) mounting concealed type, dust and vermin proof made of 16 SWG mild steel sheet cubical with double cover covering the MCB's with the locking arrangement as per drawing | [8 empty] | 1 | 1 | 18435 | 18435
- 1x 25 A TP MCCB ( Incommer)
- 3 x 3 nos. of 6 A SP MCB
- 3 x 2 nos. of 10 A SP MCB
- 3 x 3 nos. of 16 SP MCB
- 1set of 60 amp TPN copper bus bars
- 1 no of earth bus bar
- Cable gland for incoming cable
2.6 | Distribution Boards Quarter Block DB (DB6)
| Supply, installation and testing of Distribution Board in (DB) wall (flush) mounting concealed type, dust and vermin proof made of 16 SWG mild steel sheet cubical with double cover covering the MCB's with the locking arrangement as per drawing |  |  |  | 1 | [5 empty] | 1 | 20298 | 20298
30 A DP MCB (Havells)
20 A DP MCB (Havells)
4 units of energy meters ( for individual metering units)
NEA Connection Charge
2.6.1 | Qtr Junction Boards JB 61,62,63,64
| Supply, installation and testing of Junction Boardsl (flush) mounting concealed type, dust and vermin proof made of 16 SWG mild steel sheet cubical with double cover covering the MCB's with the locking arrangement as per drawing |  |  |  | 4 | [5 empty] | 4 | 3220 | 12880
- 1x 20 A SP MCCB ( Incommer)
- 2 nos. of 6 A SP MCB
- 2 nos. of 16 SP MCB
3 | Supply, Laying of 2 sets of 3.5 x952 mm Al armoured cable though the cable trench with complete cable trench works from Transformer to the Main Control Panel as per drawing and specification including cable shoes at both ends. | RM | [7 empty] | 48 | 48 | 4057 | 194736
4 | Supply, Laying of 3.5x 702 mm Cu-unarmoured cable through cable tray from Main Control Panel to the changeover switch (of Generator) and back to the control panel section B ( Complete works) as per drawing and specification including cable shoes at both ends. | rm | [7 empty] | 20 | 20 | 1536 | 30720
5 | Supply and laying of cable from MDB to Block Dist. Boards with copper conductor PVC insulated and sheathed cable through duct or PVC duct arrangements as per drawing and specification including cable shoes at both ends
5.1 | 4 x 162 mm cu- unarm cable + 1x7/20 through Underground 50 mm dia PVC conduit | rm | 41 | 68 | [6 empty] | 109 | 525 | 57225
5.2 | 2 x 7/20+ 3/22 | rm | 41 | 34 | [5 empty] | 8 | 83 | 109 | 9047
5.3 | 4 x 7/20 cable + 1x 7/22 through 25 mm dia UG PVC conduit | rm |  |  |  | 25 |  |  |  |  | 25 | 206 | 5150
5.4 | 4 x 62 mm cu- unarm cable + 1 x 7/22 through 25 mm dia UG PVC conduit | rm | [7 empty] | 8 | 8 | 302 | 2416
6 | Supply and laying of cable from Block DBs to Sub Distribution Board thought the 2 x 32 mm dia PVC conduits in room
6.1 | 4x7/18 + 1 x 7/20 cable through 32 mm dia PVC conduit | rm | 121 | 121 |  | 25 |  |  |  |  | 267 | 203 | 54201
6.2 | 2 x 7/22+1 x 1/18 | rm | 121 | 121 | 50 | 25 |  |  |  |  | 317 | 84 | 26628
7 | Supply and laying of cable from Sub DBs to Joint Boxes/Pool Boxes/Switch boxes thought the 32 mm dia PVC conduits in room
7.1 | 2 x 3/20 + 2 x 7/20 + 1 x 7/22 - Light, Power, fans | rm | 64 | 53 | 60 | 18 | 62 | 17 |  | 49 | 323 | 151 | 48773
7.2 | 2 x 7/22+1 x 1/18 - Generator ( Lights + Power) | rm | 64 | 53 |  | 18 | 62 | 17 |  | 49 | 263 | 84 | 22092
7.3 | [10 empty] | 0 | 437 | 0
8 | Supply and installation of light fixtures, point wiring from Join Box various points with 2 x 3/22 PVC insulated copper wire through 20 mm internal dia HDPE conduit concealed with switch (clipsal) as per drawing and specification including the cost of junction box and the GI Box for switch.
8.1 | 8 " flat Ceilling dome with GSL | nos. | 36 | 3 | 20 | 10 | 10 | 1 |  |  | 80 | 992 | 79360
8.2 | Wall Light fixture with 11 W PL Tube | nos. | 41 | 24 | 4 |  |  | 1 |  |  | 70 | 1084 | 75880
8.3 | Wall Light fixture with 11 W PL Tube (Self recharding / Generator) | nos. | 13 | 12 |  |  | 10 |  |  |  | 35 | 1947 | 68145
8.4 | Bulkhead Fixtures with GSL | nos. | 4 | 3 | 3 | 3 |  | 1 |  |  | 14 | 1199 | 16786
9 | Supply and installation of light fixtures, point wiring from Join Box various points with 2 x 3/22 PVC insulated copper wire through 20 mm internal dia HDPE conduit concealed with switch as per drawing and specification including the cost of junction box and the GI Box for switch.
9.1 | 1 x 40 W Celling Mounted Box Type or Mirolta type FTL with Osram Tube and Electronic ballast | nos. | 72 | 8 | 4 | 4 |  |  |  |  | 88 | 1413 | 124344
9.2 | 2 x 40 W Celling Mounted Box Type FTL with Osram Tube and Electronic ballast | nos. | 8 | 24 | [6 empty] | 32 | 2879 | 92128
9.3 | Supply , Delivery & Installation of Street lamps with 3 x 7/20 cable in 20 mm dia conduit in 8 m heigh pole with 70 W SON and street Lamp set. | nos. | [7 empty] | 7 | 7 | 15985 | 111895
10 | Supply and installation of 16 A 3pin socket point wiring with 2 x 7/22+1x 1/18 pvc insulated copper wires through 20 mm internal dia HDPE conduit concealed from Join Box to various points, along with the Switch socket (clipsal make) GI Box box, as per drawing and specification. | pts. | 128 | 47 | 21 | [5 empty] | 196 | 1073 | 210308
11 | Supply and installation of 5 A 2 pin socket point wiring with 2 x 3/20 pvc insulated copper wires through 20 mm internal dia HDPE conduit concealed from Join Box to various points, along with the Switch socket (clipsal make) GI Box box, as per drawing and specification. | pts. | 2 | 1 | 4 | [5 empty] | 7 | 615 | 4305
12 | Supply and installation of 20 A, 3 pin socket point wiring with 2 x 7/20+1x 3/20 pvc insulated copper wires through 25 mm internal dia HDPE conduit concealed from Join Box to various points, along with the DP Switch socket, GI Box as per drawing and specification. | pts. | 2 | [7 empty] | 2 | 2930 | 5860
13 | Supply and installation of 48" ceilling fan(Crompton Greaves), switch (Clipsal) , electronic regulator, wiring with 2 x 3/20 pvc insulated copper wires through 20 mm internal dia HDPE conduit along with GI Box, concealed from Join Box to various points as per drawing and specification. | pts. | 11 | 12 | 8 | [5 empty] | 31 | 2952 | 91512
14 | Supply and installation of 9 " Exhaust fan (Trans Air), switch (Clipsal), wiring with 2 x 3/20 pvc insulated copper wires through 20 mm internal dia HDPE conduit along with GI Box, concealed fromJoin Box to various points as per drawing andspecification. | pts. | 5 | 3 | 4 | 4 |  |  |  |  | 16 | 2875 | 46000
15 | Supply and installation of earth electrode made of 60cm x 60 cm x3 mm copper plate (or 3 x 4 ft. long 20 mm dia cu rod) including 8 SWG bare copper wire connectionup to MDB/ transformer neutral /generator neutral /Transformer bodyas per drawing and specification. | set |  |  | 1 |  |  |  |  | 8 | 9 | 9666 | 86994
- 1 set for Main Control Panel
- 1 set for OT supply
- 1 set each for DB X-Ray
- 1 set for Staff Qtr.
- 2 set for Generator
- 3 set for Earthing Ringmen
16 | Supply and installation of 16 mm x 3mm sizw cu- strip ringmen surrounding the hospital building and connecting 3 earth piths around the building. | rm. | 97 | 102 |  | 24 |  |  |  |  | 223 | 124 | 27652
17 | Supply and installation of 1 m long Lightening Arrestor | set | 1 | 1 | [6 empty] | 2 | 6693 | 13386
18 | Supply and installation of 25 mm x 3mm sizw cu- strip for lightening protection ( Lightening Arrestor). | m | 15 | 15 | [6 empty] | 30 | 398 | 11940
Telephone System
| Supply, Delivery, Installation and commissioning of 6 CO , 24 Extn. EPABX system, with1 hr back up with 40AH battery, surge protector, and complete accesoories including the connection in MDF | [7 empty] | 1 |  | 1 | 120290 | 120290
| Supply, Delivery, Installation and commissioning of normal DTMF Telephone set |  | 11 | 1 | 2 |  |  | 1 |  |  | 15 | 1121 | 16815
19 | Supply, Delivery & Instalaltion of 40 Pair Distribution Point ( MDF) with 12"x 8" box of 16 SWG box with crone Tag and Block, complete | set | [6 empty] | 1 |  | 1 | 4071 | 4071
20 | Supply, Delivery & Instalaltion of 20 Pair Distribution Point ( MDF) with 12"x 8" box of 16 SWG box with crone Tag and Block, complete | set | 2 | 1 | [6 empty] | 3 | 2898 | 8694
21 | Supply and installation of telephone point wiring from telephone Distribution Point (TDP) to individual point with GI Box , 3 pair communication cable through 3/4'' internal dia PVC conduit concealed as per drawing and specification. | pts | 11 | 1 | 2 |  |  | 1 |  |  | 15 | 1251 | 18765
22 | Supply, Delivery & Installation of 20 pair telecom cable in 20 mm dia PVC conduit and termination works complete. | m | [7 empty] | 351 | 351 | 189 | 66339
23 | Supply, Delivery & Installation of 10 pair telecom cable in 20 mm dia PVC conduit and termination works complete. | m | 132 | 132 | [6 empty] | 264 | 138 | 36432
24 | Supply, Delivery & Installation of 5 pair telecom cable in 20 mm dia PVC conduit and termination works complete. | m | 210 | 147 | 169 | [5 empty] | 526 | 114 | 59964
HT Transmission Lite
25 | Supply & Delivery and Installation of HT Distribution with following materials in cordination with the Electricaity Supply Authority with complete required accessories complete.
a | 80 KVA Transformer | nos | [7 empty] | 1 | 1 | 304750 | 304750
b | 11 m Steel Pole | nos | [7 empty] | 12 | 12 | 14605 | 175260
c | 5 x 2 x 2 A Bracket | nos | [7 empty] | 8 | 8 | 2559 | 20472
d | 4 x 2 x 2 Cross Arm | nos | [7 empty] | 6 | 6 | 1024 | 6144
e | 1 x 2 x 2 Top Bracket | nos | [7 empty] | 5 | 5 | 397 | 1985
f | 11 KV Disc Insulator | nos | [7 empty] | 8 | 8 | 1898 | 15184
g | 11 KV Pin Insulator | nos | [7 empty] | 24 | 24 | 282 | 6768
h | Transformer Tower Set | set | [7 empty] | 1 | 1 | 10350 | 10350
i | Earthing set | set | [7 empty] | 2 | 2 | 2300 | 4600
j | 11 KV Drop Out Fuse | set | [7 empty] | 1 | 1 | 17825 | 17825
k | 11 KV Lightening Arrestor | nos | [7 empty] | 1 | 1 | 9085 | 9085
l | Stay Set | nos | [7 empty] | 5 | 5 | 920 | 4600
m | Stay Wire | kgs | [7 empty] | 16 | 16 | 112 | 1792
n | 0.03 ACSR | m | [7 empty] | 990 | 990 | 25 | 24750
o | Stay Insulator | nos | [7 empty] | 5 | 5 | 117 | 585
p | LV Distribution Board, 125 A TPN MCCB | nos | [7 empty] | 1 | 1 | 4600 | 4600
q | 125 A TPN MCCB | nos | [7 empty] | 1 | 1 | 17710 | 17710
r | L/V , 4 core 1202 mm Al armoured cable | m | [7 empty] | 60 | 60 | 621 | 37260
s | Cable Shoe | nos | [7 empty] | 20 | 20 | 74.75 | 1495
2899968

## Rate Ana_ Elect (hidden)
Rate Analysis _ Main Supply Cables
S.N | Description | Unit | qty | Material |  | Labour |  | S Total | OH & P | G Total
|  |  |  | Rate | Amount | Rate | Amount |  | 15%
A
1 | Transformer to Main Distribuiton Board,
| 2 x 952 mm Cu-Armoured cable | 2 | m | 1584 | 3168 | 75 | 150
| Cable shoes and accessories | 4 | ls | 45 | 180 | 7.5 | 30
[5 empty] | 3348 |  | 180 | 3528 | 529.2 | 4057.2
2 | MDB to Changeover back to MCB
| 3.5 x 70 Sq. mm cu cable | 1 | m | 1080 | 1080 | 70 | 70
| 50 mm dia duct | 1 | ls | 36 | 36 | 10 | 10
| Cable shoe | 4 | nos | 25 | 100 | 10 | 40
[5 empty] | 1216 |  | 120 | 1336 | 200.4 | 1536.4
| 4 x 162 mm cu- unarm cable | 1 | m | 320 | 320 | 20 | 20
| 1 x 7/20 | 1 | m | 28.7 | 28.7 | 8 | 8
| 50 mm PVC Conduit | 1 | m | 32 | 32 | 6 | 6
| Digging Refilling work | 0.09 | cm |  | 0 | 185 | 16.65
| Accessories | 1 | lot | 15 | 15 | 10 | 10
[5 empty] | 395.7 |  | 60.65 | 456.35 | 68.4525 | 524.8025
| 4 x 102 mm cu- unarm cable | 1 | m | 215 | 215 | 20 | 20
| 8 SWG Cu wire | 1 | m | 58 | 58 | 8 | 8
| 32 mm PVC Conduit | 1 | m | 27 | 27 | 10 | 10
| Digging Refilling work | 0.09 | cm |  | 0 | 185 | 16.65
| Accessories | 1 | lot | 15 | 15 | 10 | 10
[5 empty] | 315 |  | 64.65 | 379.65 | 56.9475 | 436.5975
| 4 x 62 mm cu- unarm cable | 1 | m | 144 | 144 | 15 | 15
| 1 x 7/22 | 1 | m | 18.7 | 18.7 | 6 | 6
| 32 mm PVC Conduit | 1 | m | 27 | 27 | 10 | 10
| Digging Refilling work | 0.09 | cm |  | 0 | 185 | 16.65
| Accessories | 1 | lot | 15 | 15 | 10 | 10
[5 empty] | 204.7 |  | 57.65 | 262.35 | 39.3525 | 301.7025
| 4 x 7/18 | 4 | m | 28.43 | 113.72 | 4 | 16
| 1 x 7/20 PVC | 1 | m | 18.4 | 18.4 | 3 | 3
| (20 mm dia PVC duct) | 1 | ls | 21 | 21 | 4 | 4
[5 empty] | 153.12 |  | 23 | 176.12 | 26.418 | 202.538
| 20mm HDPE conduit | m | 1 | 14 | 14 | 3 | 3
| 4 x 7/20 | m | 4 | 28.7 | 114.8 | 6 | 24
| 1 x 7/22 | m | 1 | 18.7 | 18.7 | 5 | 5
[5 empty] | 147.5 |  | 32 | 179.5 | 26.925 | 206.425
| 20mm HDPE conduit | m | 1 | 14 | 14 | 3 | 3
| 2 x 7/20 | m | 2 | 28.7 | 57.4 | 6 | 12
| 1 x 3/22 | m | 1 | 5.46 | 5.46 | 3 | 3
[5 empty] | 76.86 |  | 18 | 94.86 | 14.229 | 109.089
| 20mm HDPE conduit | m | 1 | 14 | 14 | 3 | 3
| 4 x 7/22 | m | 2 | 21 | 42 | 4 | 8
| 1 x1/18 | m | 1 | 3.26 | 3.26 | 3 | 3
[5 empty] | 59.26 |  | 14 | 73.26 | 10.989 | 84.249
| 20mm HDPE conduit | m | 1 | 14 | 14 | 3 | 3
| 2 x 7/20 | m | 2 | 28.7 | 57.4 | 6 | 12
| 1 x 7/22 | m | 1 | 18.7 | 18.7 | 3 | 3
| 2 x 3/20 | m | 2 | 8.53 | 17.06 | 3 | 6
[5 empty] | 107.16 |  | 24 | 131.16 | 19.674 | 150.834
| 20mm HDPE conduit | m | 1 | 14 | 14 | 3 | 3
| 1 x 7/22 | m | 2 | 18.7 | 37.4 | 4 | 8
| 1 x1/18 | m | 1 | 3.26 | 3.26 | 3 | 3
[5 empty] | 54.66 |  | 14 | 68.66 | 10.299 | 78.959
Rate Analysis - Dist. Boards
S.N | Description | Unit | qty | Material |  | Labour |  | S Total | OH & P | G Total
|  |  |  | Rate | Amount | Rate | Amount |  | 15%
1 | Main Distribution Board | nos | 1 | 11500 | 11500 | 8500 | 8500
| 1 x 150A TP MCCB | nos | 1 | 14500 | 14500
| 1 x 60 A TP+N Changeover Switch | nos | 1 | 14500 | 14500
| 3 x 50 A TP MCCB | nos | 1 | 3250 | 3250
| 3 x 30 A TP MCCB | nos | 3 | 3000 | 9000
| 3 x 20 A TP MCCB | nos | 3 | 3000 | 9000
| 2 x 25 A TP MCB | nos | 2 | 1200 | 2400
| 2 x 20 A TP MCB | nos | 2 | 1200 | 2400
| 2 x 16 A TP MCB | nos | 2 | 1200 | 2400
| 1 set of 300 amp TPN copper bus bars | set | 4 | 700 | 2800
| 1 set of 120 amp DP copper bus bars | set | 2 | 450 | 900
| 2 set of earth bus bar |  | 2 | 450 | 900
| 1 set of HRC Fuse | nos | 3 | 150 | 450
| 2 set of Voltmeter with selector switch | nos | 2 | 550 | 1100
| 1 set of 200 Amp ammeter with selector switch | nos | 1 | 550 | 550
| 1 set of 50 Amp ammeter with selector switch | nos | 1 | 550 | 550
| Required CT's | nos | 3 | 250 | 750
| Indicator Lamps | nos | 3 | 200 | 600
[5 empty] | 77550 |  | 8500 | 86050 | 12907.5 | 98957.5
2 | Block Distribution Board
2.1 | DB Medical / Mixed
| Metal Box | no | 1 | 7000 | 7000 | 5500 | 5500
| 1 no. of 40 A TP MCB (Havells) | no | 1 | 1200 | 1200
| 4 nos. of 32 A TP MCB Halvells | no | 1 | 1200 | 1200
| 1 no of 25 A TP MCB ( Havells) | no | 3 | 1200 | 3600
| 4 nos. of 20 A TP MCB Halvells | set | 1 | 1200 | 1200
| - 1 set of 100 amp TPN copper bus bars | nos | 4 | 250 | 1000
| - 1 set of 75 amp TPN copper bus bars | nos | 2 | 200 | 400
| - 2 no of earth bus bar | set | 2 | 200 | 400
| Cable Shoe with shoe | set | 15 | 20 | 300
| Indicator Lamps | nos | 3 | 200 | 600
[5 empty] | 16300 |  | 5500 | 21800 | 3270 | 25070
3.2 | Outdoor DB
| Metal Box | no | 1 | 4500 | 4500 | 4500 | 4500
| 20 A TP MCB (Havells) | no | 1 | 1200 | 1200
| 16 A DP MCB ( Havells) | no | 3 | 650 | 1950
| 16 A SP MCB Halvells | no | 9 | 120 | 1080
| 10 A SP MCB Halvells | no | 6 | 120 | 720
| 6 A SP MCB Halvells | no | 9 | 120 | 1080
| - 1 set of 60 amp TPN copper bus bars | set | 4 | 250 | 1000
| - 1 no of earth bus bar | set | 1 | 200 | 200
| Cable Shoe | set | 15 | 20 | 300
| Indicator Lamps | nos | 3 | 200 | 600
[5 empty] | 11530 |  | 4500 | 16030 | 2404.5 | 18434.5
DB - X Ray
| Board | no | 1 | 4500 | 4500 | 4500 | 4500
| 30 A TP MCCB | no | 1 | 3000 | 3000
| 25 A TP MCB Halvells | no | 3 | 1200 | 3600
| 16 A TP MCB Halvells | no | 3 | 1200 | 3600
| - 1 set of 80 amp TPN copper bus bars | no | 4 | 250 | 1000
| - 1 no of earth bus bar | no | 1 | 200 | 200
| Cable Shoe | set | 15 | 20 | 300
| - 1 set of Indicator Lamp | no | 3 | 200 | 600
[5 empty] | 15900 |  | 4500 | 20400 | 3060 | 23460
DB - Toilet Block
| Board | no | 1 | 2500 | 2500 | 2500 | 2500
| 16 A TP MCB (Havells) | no | 1 | 1200 | 1200
| 6 nos. of 16 A SP MCB Halvells | no | 6 | 120 | 720
| 3 nos. of 6 A SP MCB Halvells | no | 3 | 120 | 360
| - 1 set of 60 amp TPN copper bus bars | nos | 4 | 200 | 800
| - 1 no of earth bus bar | no | 1 | 150 | 150
[5 empty] | 5730 |  | 2500 | 8230 | 1234.5 | 9464.5
DB Quarter
| Board | no | 1 | 2500 | 2500 | 1500 | 1500
| 30 A DP MCB (Havells) | no | 1 | 650 | 650
| 20 A DP MCB (Havells) | no | 4 | 650 | 2600
| Energy meter | no | 4 | 1800 | 7200
| NEA Connection Charge | set | 1 | 3200 | 3200
[5 empty] | 16150 |  | 1500 | 17650 | 2647.5 | 20297.5
3.3 | Sub Distribution Board 21,23,24, 31,32,33,34,
| Metal Box | no | 1 | 4500 | 4500 | 4500 | 4500
| 20 A TP MCB (Havells) | no | 1 | 1200 | 1200
| 16 A DP MCB ( Havells) | no | 1 | 650 | 650
| 12 nos. of 16 A SP MCB Halvells | no | 12 | 120 | 1440
| 6 nos. of 10 A SP MCB Halvells | no | 6 | 120 | 720
| 3 nos. of 6 A SP MCB Halvells | no | 12 | 120 | 1440
| - 1 set of 60 amp TPN copper bus bars | no | 4 | 250 | 1000
| - 1 set of 45 amp P+N copper bus bars | no | 4 | 200 | 800
| - 2 no of earth bus bar | no | 2 | 150 | 300
[5 empty] | 12050 |  | 4500 | 16550 | 2482.5 | 19032.5
3.4 | Sub Distribution Board 2_ Hospital
| Metal Box | no | 1 | 4500 | 4500 | 4500 | 4500
| 25 A TP MCB (Havells) | no | 1 | 1200 | 1200
| 16 A DP MCB ( Havells) | no | 1 | 650 | 650
| 12 nos. of 16 A SP MCB Halvells | no | 12 | 120 | 1440
| 6 nos. of 10 A SP MCB Halvells | no | 6 | 120 | 720
| 12 nos. of 6 A SP MCB Halvells | no | 12 | 120 | 1440
| - 1 set of 60 amp TPN copper bus bars | no | 4 | 250 | 1000
| - 1 set of 45 amp P+N copper bus bars | no | 4 | 200 | 800
| - 1 no of earth bus bar | no | 2 | 150 | 300
[5 empty] | 12050 |  | 4500 | 16550 | 2482.5 | 19032.5
Quarter Junction Board ( Indivisual Qtrs)
| Board | no | 1 | 1200 | 1200 | 1000 | 1000
| 20 A SP MCB (Havells) | no | 1 | 120 | 120
| 16 A SP MCB Halvells | no | 2 | 120 | 240
| 6 A SP MCB Halvells | no | 2 | 120 | 240
[5 empty] | 1800 |  | 1000 | 2800 | 420 | 3220
4 | Telephone
4.1 | 40 pair Main Distribution Frame (MDF)
| 16 SWG MS Box ( 12" x 8") | no | 1 | 1000 | 1000 | 500 | 500
| 4 x 10 pair Krone Tag | no | 4 | 350 | 1400 | 100 | 400
| Tag Block | set | 4 | 30 | 120 | 20 | 80
| Accessories | ls | 1 | 30 | 30 | 10 | 10
[5 empty] | 2550 |  | 990 | 3540 | 531 | 4071
4.2 | Distibution Points (DP)
4.2.1 | 20 pair ( 12" x 8")
| 16 SWG MS Box | no | 1 | 1000 | 1000 | 500 | 500
| 2 x 10 pair Krone Tag | no | 2 | 350 | 700 | 100 | 200
| Tag Block | set | 2 | 30 | 60 | 20 | 40
| Accessories | ls | 1 | 15 | 15 | 5 | 5
[5 empty] | 1775 |  | 745 | 2520 | 378 | 2898
4.2.2 | 10 pair ( 12" x 8")
| 16 SWG MS Box | no | 1 | 1000 | 1000 | 500 | 500
| 1 x 10 pair Krone Tag | no | 1 | 350 | 350 | 100 | 100
| Tag Block | set | 1 | 30 | 30 | 20 | 20
| Accessories | ls | 1 | 15 | 15 | 5 | 5
[5 empty] | 1395 |  | 625 | 2020 | 303 | 2323
4.3 | Telecom Cable (MDF to DP's)
4.3.1 | 20 pairs
| 25 mm conduit | m | 1 | 19 | 19 | 4 | 4
| 1 x 20 pair cable | m | 1 | 94.5 | 94.5 | 15 | 15
| Chieseling redoing | rm | 1 | 15 | 15 | 5 | 5
| Accessories | ls | 1 | 2 | 2 | 10 | 10
[5 empty] | 130.5 |  | 34 | 164.5 | 24.675 | 189.175
4.3.2 | 10 pair
| 20 mm conduit | m | 1 | 12 | 12 | 4 | 4
| 1 x 10 pair cable | m | 1 | 57 | 57 | 15 | 15
| Chieseling redoing | rm | 1 | 15 | 15 | 5 | 5
| Accessories | ls | 1 | 2 | 2 | 10 | 10
[5 empty] | 86 |  | 34 | 120 | 18 | 138
4.3.2 | 5pair
| 20 mm conduit | m | 1 | 12 | 12 | 4 | 4
| 1 x 5 pair cable | m | 1 | 36 | 36 | 15 | 15
| Chieseling redoing | rm | 1 | 15 | 15 | 5 | 5
| Accessories | ls | 1 | 2 | 2 | 10 | 10
[5 empty] | 65 |  | 34 | 99 | 14.85 | 113.85
Rate Analysis _ Point to Point Wiring
S.N | Description | Unit | qty | Material |  | Labour |  | S Total |  | OH & P | G Total
|  |  |  | Rate | Amount | Rate | Amount |  |  | 15%
1 | Light Point ( 2 wire)
| 20 mm conduit | m | 7 | 14 | 98 | 3 | 21
| 2 x 3/22 | m | 15 | 5.58 | 83.7 | 2 | 30
| metal box fitting | nos | 1 | 16 | 16 | 15 | 15
| Chieseling redoing (with cement mortars) | rm | 6 | 0 | 0 | 4 | 24
| Switch fitting | nos | 1 | 90 | 90 | 15 | 15
[5 empty] | 287.7 |  | 105 | 392.7 |  | 58.905 | 451.605
Light Point ( 3 wire)
| 20 mm conduit | m | 7 | 14 | 98 | 3 | 21
| 3 x 3/22 | m | 23 | 5.58 | 128.34 | 2 | 46
| metal box fitting | nos | 1 | 16 | 16 | 15 | 15
| Chieseling redoing (with cement mortars) | rm | 6 | 0 | 0 | 4 | 24
| Switch fitting | nos | 1 | 90 | 90 | 15 | 15
[5 empty] | 332.34 |  | 121 | 453.34 |  | 68.001 | 521.341
1.1 | 8 " flat Ceilling dome with 60W Indcasent Lamp | nos. | 1 | 450 | 450 | 20 | 20 | 470 | 862.7 | 129.405 | 992.105
1.2 | Wall Fixture with 11 W Pl Tube | nos. | 1 | 525 | 525 | 25 | 25 | 550 | 942.7 | 141.405 | 1084.105
1.3 | Independent Emergency lights Wall Fixture with 11 W Pl Tube | nos. | 1 | 1200 | 1200 | 100 | 100 | 1300 | 1692.7 | 253.905 | 1946.605
1.4 | 1 x 40 W FLT Box Type / Mirolta Type for wall mounting purpose | nos. | 1 | 650 | 650 | 125 | 125 | 775 | 1228.34 | 184.251 | 1412.591
1.5 | 1 x 40 W Surface (celling) Mounted acrylic cover 2 nos of hanging arrangement | nos. | 1 | 1200 | 1200 | 125 | 125 | 1325 | 1778.34 | 266.751 | 2045.091
1.6 | 2 x 40 W Surface (ceilling) Mounted Acrylic cover 2 nos of hanging arrangement | nos. | 1 | 1850 | 1850 | 200 | 200 | 2050 | 2503.34 | 375.501 | 2878.841
1.7 | 4 x 60 W Ceilling dome with GSL lamps | nos. | 1 | 1740 | 1740 | 100 | 100 | 1840 | 2232.7 | 334.905 | 2567.605
1.8 | 1x 60 w GLS lamp in Bulhead fixture | nos. | 1 | 625 | 625 | 25 | 25 | 650 | 1042.7 | 156.405 | 1199.105
| Bathroom Mirror light with GSL | nos. | 1 | 600 | 600 | 25 | 25 | 625 | 1017.7 | 152.655 | 1170.355
| Picture Light at Lobby with GSL (optional) | nos. | 1 | 850 | 850 | 40 | 40 | 890 | 1282.7 | 192.405 | 1475.105
| Bulkhead Fixtures with GSL | nos. | 1 | 625 | 625 | 25 | 25 | 650 | 1042.7 | 156.405 | 1199.105
1.9 | Supply , Delivery & Installation of Street lamps with 2 x 7/20 cable in 20 mm dia conduit in 8 m heigh pole with 125 W street Lamps. | nos. | 1 | 6900 | 6900 | 1250 | 1250 | 8150 | 10200 | 1530 | 11730
1.1 | Supply , Delivery & Installation of gate light ( Stand fixture with vandal proof Net & GLS) with 2 x 3/20 cable in 20 mm dia conduit in 2" dia MS steel pipe of 7 ft height with proper earth work ( as per the desigh and drawing) | nos. | 1 | 1530 | 1530 | 700 | 700 | 2230 | 4070 | 610.5 | 4680.5
2 | 2 way Light Point
2.1 | 20 mm conduit | m | 15 | 14 | 210 | 3 | 45
| 3 x 3/22 | m | 45 | 5.58 | 251.1 | 1.1 | 49.5
| metal box fitting | nos | 2 | 16 | 32 | 10 | 20
| Chieseling redoing | rm | 10 | 6 | 60 | 3 | 30
| Switch fitting | nos | 2 | 120 | 240 | 10 | 20
[5 empty] | 793.1 |  | 164.5 | 957.6 |  | 143.64 | 1101.24
3 | Outdoor Lights ( Gate Lights)
| 20 mm conduit | m | 11 | 14 | 154 | 4 | 44
| 2 x 3/22 | m | 14 | 5.58 | 78.12 | 1.5 | 21
| metal box fitting | nos | 1 | 16 | 16 | 15 | 15
| Chieseling redoing (with cement mortars) | rm | 7 | 0 | 0 | 0 | 0
| 2" dia MS pipe - 7ft length | no | 1 | 250 | 250 | 300 | 300
| 12" dia Poly globe Fixture with GLS | set | 1 | 750 | 750 | 75 | 75
| Switch fitting (Clipsal make) | nos | 1 | 75 | 75 | 10 | 10
[5 empty] | 1323.12 |  | 465 | 1788.12 |  | 268.218 | 2056.338
4 | Street Light Fitting
| 20 mm conduit | m | 25 | 14 | 350 | 4 | 100
| 2 core 1.5 Sq. mm cu unarmoured cable | m | 44 | 36 | 1584 | 1.5 | 66
| Marshalling Box | nos | 1 | 700 | 700 | 150 | 150
| street Lamp with 70 W SON Light | nos | 1 | 4100 | 4100 | 850 | 850
| 8 m ht. pole | no | 1 | 4500 | 4500 | 1100 | 1100
| Switch fitting | nos | 1 | 350 | 350 | 50 | 50
[5 empty] | 11584 |  | 2316 | 13900 |  | 2085 | 15985
5 A Power socket
| 20 mm conduit | m | 5 | 16 | 80 | 3 | 15
| 3 x 3/22 | m | 12 | 16 | 192 | 1.1 | 13.2
| metal box fitting | nos | 1 | 15 | 15 | 15 | 15
| Chieseling redoing | rm | 7 | 6 | 42 | 4 | 28
| Switch socket fitting | nos | 1 | 90 | 90 | 45 | 45
[5 empty] | 419 |  | 116.2 | 535.2 |  | 80.28 | 615.48
5 | 15 A Power socket
| 20 mm conduit | m | 7 | 14 | 98 | 3 | 21
| 2 x 7/22 | m | 16 | 18.7 | 299.2 | 2 | 32
| 1 x 1/18 | m | 8 | 3.2 | 25.6 | 1.5 | 12
| metal box fitting | nos | 1 | 15 | 15 | 15 | 15
| Chieseling redoing | rm | 7 | 6 | 42 | 4 | 28
| Switch socket fitting | nos | 1 | 300 | 300 | 45 | 45
[5 empty] | 779.8 |  | 153 | 932.8 |  | 139.92 | 1072.72
6 | Ceilling Fan Fitting
| 20 mm conduit | m | 6 | 14 | 84 | 4 | 24
| 2 x 3/20 | m | 12 | 8.55 | 102.6 | 1.75 | 21
| metal box fitting | nos | 1 | 20 | 20 | 15 | 15
| Chieseling redoing | rm | 5 | 15 | 75 | 5 | 25
| Expansion Bolt fitting/ Clamping in ceilling | no | 1 | 100 | 100 | 50 | 50
| 48" ceilling fan with regulator ( CG) | no | 1 | 1950 | 1950 | 100 | 100
[5 empty] | 2331.6 |  | 235 | 2566.6 |  | 384.99 | 2951.59
7 | Exhaust Fan Fitting
| 20 mm conduit | m | 7 | 14 | 98 | 4 | 28
| 2 x 3/20 | m | 14 | 8.55 | 119.7 | 1.75 | 24.5
| metal box fitting | nos | 1 | 20 | 20 | 15 | 15
| Chieseling redoing | rm | 4 | 15 | 60 | 5 | 20
| switch (Clipsal) | nos | 1 | 75 | 75 | 15 | 15
| Boxing & Bolting | no | 1 | 100 | 100 | 50 | 50
| 9" Exhaust Fan ( Trans air, CG) | no | 1 | 1800 | 1800 | 75 | 75
[5 empty] | 2272.7 |  | 227.5 | 2500.2 |  | 375.03 | 2875.23
8 | 20 A Power for A/C
| 20 mm conduit | m | 18 | 14 | 252 | 4 | 72
| 2 x 7/20 | m | 36 | 18.7 | 673.2 | 5 | 180
| 1 x 3/20 | m | 18 | 8.55 | 153.9 | 4 | 72
| metal box fitting | nos | 1 | 20 | 20 | 15 | 15
| Chieseling redoing | rm | 18 | 15 | 270 | 5 | 90
| DP Switch socket with indicator fitting | nos | 1 | 700 | 700 | 50 | 50
[5 empty] | 2069.1 |  | 479 | 2548.1 |  | 382.215 | 2930.315
9 | Telephone
| 20 mm conduit | m | 21 | 14 | 294 | 4 | 84
| 3 pair communication cable | m | 20 | 7.5 | 150 | 3 | 60
| metal box | nos | 1 | 20 | 20 | 15 | 15
| Chieseling redoing | rm | 10 | 15 | 150 | 5 | 50
| Telephone socket fitting | nos | 1 | 190 | 190 | 75 | 75
[5 empty] | 804 |  | 284 | 1088 |  | 163.2 | 1251.2
10 | Cu Plate Earthing
| 60 x 60 x 3 mm cu plate | nos | 1 | 3600 | 3600 | 100 | 100
| nut bolt/ brazing | lot | 1 | 200 | 200 | 150 | 150
| excavation & refilling | m3 | 7 |  | 0 | 185 | 1295
| common salt | kgs | 400 | 2 | 800 |  | 0
| charcoal | kgs | 200 | 8 | 1600 |  | 0
| 8 SWG bare cu wire | m | 30 | 12 | 360 | 10 | 300
[5 empty] | 6560 |  | 1845 | 8405 |  | 1260.75 | 9665.75
11 | Lightening Arrester
| 2 m long Lightening Arrester made of pure copper | nos | 1 | 5200 | 5200 | 300 | 300
| Fixxing accessories | lot | 1 | 270 | 270 | 50 | 50
[5 empty] | 5470 |  | 350 | 5820 |  | 873 | 6693
12 | Cu- strip for Lightening Arrestor
| 25 mm x 2 mm pure cu strip | m | 1 | 245 | 245 | 60 | 60
| Cu / Brass saddle | no | 1 | 16 | 16 | 10 | 10
| Accessories | lot | 1 | 10 | 10 | 5 | 5
[5 empty] | 271 |  | 75 | 346 |  | 51.9 | 397.9
13 | Cu Strip Ringmen Earthing
| 16 mm x 2 mm cu strip | m | 1 | 36 | 36
| Cu- nut Bolts | nos | 0.05 | 18 | 0.9
| Brazing | LS | 1 |  |  | 15 | 15
| Digging & Refilling .7 m x .25 x 1.m | cu.m | 0.3 |  |  | 186 | 55.8
[5 empty] | 36.9 |  | 70.8 | 107.7 |  | 16.155 | 123.855
14 | Telephone set
| normal DTMF telephone set | no | 1 | 900 | 900 | 75 | 75
[5 empty] | 900 |  | 75 | 975 |  | 146.25 | 1121.25
15 | Aircon units
| 18000 BTU/Hr split type aircondition unit | set | 1 | 64000 | 64000 | 5000 | 5000
[5 empty] | 64000 |  | 5000 | 69000 |  | 10350 | 79350
16 | PABX
| 6 Co line and 24 Extension capacity PABX | set | 1 | 69000 | 69000 | 6900 | 6900
| Surge Protector |  | 1 | 3000 | 3000 | 1000 | 1000
| Back Up 1hr. 40 Amp |  | 1 | 6200 | 6200 | 1000 | 1000
| Acessories | ls | 1 | 5000 | 5000 | 500 | 500
| Installation and commissioning | set | 1 |  | 0 | 12000 | 12000
[5 empty] | 83200 |  | 21400 | 104600 |  | 15690 | 120290
17 | Voltage Stabilizer
| 5 KVA capacity Voltage Stabilizer | set | 1 | 82000 | 82000 | 5000 | 5000
| Acessories | LS | 1 | 5000 | 5000 | 250 | 250
| Installation and commissioning | set | 1 |  | 0 | 500 | 500
[5 empty] | 87000 |  | 5750 | 92750 |  | 13912.5 | 106662.5
HT Line
1 | 80 KVA Transformer | nos | 1 | 124000 | 124000 | 25000 | 25000 | 149000 | 22350 | 171350
2 | 11 m Steel Pole | nos | 1 | 142 | 142 | 1000 | 1000 | 1142 | 171.3 | 1313.3
3 | 5 x 2 x 2 A Bracket | nos | 1 | 2000 | 2000 | 225 | 225 | 2225 | 333.75 | 2558.75
4 | 4 x 2 x 2 Cross Arm | nos | 1 | 800 | 800 | 90 | 90 | 890 | 133.5 | 1023.5
5 | 1 x 2 x 2 Top Bracket | nos | 1 | 300 | 300 | 45 | 45 | 345 | 51.75 | 396.75
6 | 11 KV Disc Insulator | nos | 1 | 1450 | 1450 | 200 | 200 | 1650 | 247.5 | 1897.5
7 | 11 KV Pin Insulator | nos | 1 | 220 | 220 | 25 | 25 | 245 | 36.75 | 281.75
8 | Transformer Tower Set | set | 1 | 8000 | 8000 | 1000 | 1000 | 9000 | 1350 | 10350
9 | Earthing set | set | 1 | 1500 | 1500 | 500 | 500 | 2000 | 300 | 2300
10 | 11 KV Drop Out Fuse | set | 1 | 9000 | 9000 | 1500 | 1500 | 10500 | 1575 | 12075
11 | 11 KV Lightening Arrestor | nos | 1 | 7000 | 7000 | 900 | 900 | 7900 | 1185 | 9085
12 | Stay Set | nos | 1 | 700 | 700 | 100 | 100 | 800 | 120 | 920
13 | Stay Wire | kgs | 1 | 72 | 72 | 25 | 25 | 97 | 14.55 | 111.55
14 | 0.03 ACSR | m | 1 | 21 | 21 | 5 | 5 | 26 | 3.9 | 29.9
15 | Stay Insulator | nos | 1 | 82 | 82 | 20 | 20 | 102 | 15.3 | 117.3
16 | LV Distribution Board | nos | 1 | 3000 | 3000 | 1000 | 1000 | 4000 | 600 | 4600
17 | 125 A TPN MCCB |  | 1 | 9000 | 9000 | 1400 | 1400 | 10400 | 1560 | 11960
18 | L/V , 4 core 1202 mm Al armoured cable | m | 1 | 450 | 450 | 90 | 90 | 540 | 81 | 621
19 | Cable Shoe |  | 1 | 45 | 45 | 20 | 20 | 65 | 9.75 | 74.75

## Sheet1 (hidden)
MECHINAGAR MUNICIPALITY
RATES WITH TRANSPORTATION COSTS
Basis:
| Speed | 20 | Km/h
| Detention | 0.75 | Hour
| Rate | 459.67 | Rs./hour
| Labour | 90 | Rs./Day
| Load/ Unload Coefficient | 0.41
a) Boulder
| Distance |  | 12 | km
| Labour |  | 1.4 | MD
| Carriage Capacity for Boulder |  | 3.5 | Cum
1 | Transportation Cost | Rs. | 896.36
2 | Collection | Rs. | 441
3 | Load/ Unload | Rs. | 86.4
4 | Local Tax | Rs. | 110
| Total | Rs. |  | 1533.76
| Per Cum Rate |  |  | 438.22
b) Sand
| Distance |  | 5 | km
| Labour |  | 1.43 | MD
| Carriage Capacity for Boulder |  | 5.38 | Cum
1 | Transportation Cost | Rs. | 574.59
2 | Collection | Rs. | 692.41
4 | Local Tax | Rs. | 80
| Total | Rs. |  | 1347
| Per Cum Rate |  |  | 250.37
c) Soil
| Distance |  | 10 | km
| Labour |  | 0.7 | MD
| Carriage Capacity for Boulder |  | 5 | Cum
1 | Transportation Cost | Rs. | 804.42
2 | Cutting Charge | Rs. | 63
3 | Soil Cost | Rs. | 200
| Total | Rs. |  | 1067.42
| Per Cum Rate |  |  | 213.48
| Door | 7100
| Window | 5200
| Ventilation | 4500